**MENTAL HEALTH HOMICIDE**

* The Mental Health Homicide Review Task and Finish group have provided the SUSR team with an Annex which explains how this will fit into the SUSR process. This will be included in the SUSR Toolkit.

**WALES SAFEGUARDING REPOSITORY**

* A WSR Delivery Group meeting was held to decide next steps.
* It was agreed that the SUSR Report template would be worked on further to ensure its compatibility with the WSR.

**POLICY & PROCESS**

* Work will continue on the SUSR Report template. The final version will be signed off by stakeholders, including the Home Office.

**LEGAL & GOVERNANCE**

* Key conversations held with Welsh Government Assurance and Data Sharing teams which have determined that WG cannot endorse the WASPI DDA. Project Manager now working with Head of Data Sharing to determine which route will suffice to provide Health Boards assurance they need to provide patient record information for purposes of SUSR.

**PROGRESS**

* As the project approaches formal consultation, the Task and Finish groups may find that they have completed the work that they set out to accomplish. The SUSR team are keen to continue contact with all partners through a **Stakeholder Reference Group**. This will ensure that members of the Task and Finish groups will keep their role as critical friends of the SUSR project as a whole.

**LEARNING & TRAINING**

* A meeting with one of the Regional Safeguarding Boards was held to discuss a way forward for the creation of the SUSR Training materials. Further research into the most suitable approach will now be conducted.

**OFFENSIVE WEAPON HOMICIDE**

* This group will soon be presented with a tabletop exercise which considers the Welsh SUSR/OWHR pilot.
* The Home Office OWHR team have provided further comments to ensure that the SUSR Statutory Guidance properly captures the OWHR process.

**SUSR STATUTORY GUIDANCE**

* The pre-consultation engagement sessions where held last week. Over 190 stakeholders were invited to comment on the draft Statutory Guidance during this period. These comments are now being analysed by the SUSR team and amendments are being made where appropriate.
* Once the amendments have been made, the draft will then be circulated with the SUSR Steering Group before the formal consultation commences.

**This document is also available in Welsh**

**BACKGROUND**

Create a single review process where a multi-agency approach is required, incorporating the following review processes Adult Practice Review; Child Practice Review; Domestic Homicide Review; Mental health Homicide Review; Offensive Weapon Homicide Review. The final report is then used to inform professional practice via the Wales Safeguarding

Repository.

**1**

**SUSR**

**UPDATE**

**BRIEFING**

**7**

**6**

**5**

**2**

**3**

**4**

If you have any questions or comments, please email: [SUSRWales@gov.wales](mailto:SUSRWales@gov.wales)

**7 MINUTE BRIEFING**

**5**